## 10-Day Task List
CaseXellence – 10-Day Development Task List
Stack: Strapi 5 ¦ .NET 10 BFF ¦ Angular 19 SSR ¦ Redis / HybridCache
Day | Area | Task | Notes | Est. Hours
Day 0 | Learning | Dynamic Zones deep-dive | Read Strapi docs on Content Types, Components, and Dynamic Zones. Understand __component field in REST response. | 3
| Learning | Dynamic Zones hands-on lab | Build a throwaway Strapi project with 1 Content Type + Dynamic Zone + 3 Components. Call populate=* and inspect JSON. | 3
| Learning | Flexible API & caching concepts | Understand JsonElement passthrough design. Review HybridCache L1/L2 TTL and ISR stale-while-revalidate pattern. | 2
Day 1 | Setup | Local environment setup | Install Homebrew, Redis, Node.js, Strapi 5 globally. | 2
| Strapi | Create Strapi 5 project | npx create-strapi-app@latest casex-cms, run on :1337. | 1
| Strapi | Create Content Types | Create Page content type with title, slug, publishedAt. | 2
| Strapi | Create Components & Dynamic Zone | Create HeroBanner, RichText, ImageGallery. Add 'sections' Dynamic Zone to Page. | 3
Day 2 | Strapi | Add dummy content | Create Home and About pages using all 3 components. | 2
| Strapi | Test Strapi REST API | GET /api/pages?populate=* — verify __component field appears in each section. | 2
| Strapi | Configure Webhook | Settings → Webhooks → URL: localhost:5000/api/webhook/purge ¦ Trigger: Entry Published. | 2
| Strapi | Document API response | Save sample populate=* response. Note __component values — Angular will match these. | 2
Day 3 | NET BFF | Create .NET 10 Minimal API project | Single endpoint GET /api/content?contentType=&slug= handles all pages. No endpoint per page. | 2
| NET BFF | Install NuGet packages | Microsoft.Extensions.Caching.Hybrid, StackExchange.Redis, Microsoft.Extensions.Caching.StackExchangeRedis. | 1
| NET BFF | Create flexible response model | PageResponse with Title, Slug, JsonElement Sections. No typed DTOs per component. | 2
| NET BFF | Create StrapiService | GetContentAsync(contentType, slug) builds URL dynamically with populate=*. Returns raw JSON, no mapping. | 3
Day 4 | NET BFF | Setup Redis + HybridCache | Configure Redis and HybridCache in appsettings.json and Program.cs. | 2
| NET BFF | Create ContentCacheService | GetOrCreateAsync with key format contentType:slug. L1 RAM=30s, Soft TTL=4min, L2 Redis=5min. | 3
| NET BFF | Implement ISR background refresh | Task.Run stale-while-revalidate: serve stale instantly, refresh cache in background. | 3
Day 5 | NET BFF | Create WebhookController | POST /api/webhook/purge. Receives contentType + slug, calls hybridCache.RemoveAsync. | 2
| NET BFF | Test full .NET flow | Cold request hits Strapi, warm request served from cache. Verify with redis-cli keys *. | 2
| NET BFF | Test webhook purge | POST to purge endpoint → Redis key deleted → next request re-fetches from Strapi. | 2
| NET BFF | Error handling + logging | Handle Strapi down and Redis down gracefully. Add ILogger throughout. | 2
Day 6 | Angular | Create Angular 19 SSR project | ng new casex-portal --ssr. Review server.ts, app.config.server.ts, main.server.ts. | 2
| Angular | Setup Cache-Control header | Set Cache-Control: public, max-age=60, stale-while-revalidate=30 in server.ts. | 2
| Angular | Create ApiService | getContent(contentType, slug) calls GET /api/content. Returns Observable<any>, no typed interface. | 2
| Angular | Test Angular SSR renders | Build and view page source — confirm full HTML is rendered server-side. | 2
Day 7 | Angular | Create base components | HeroBannerComponent, RichTextComponent, ImageGalleryComponent — each accepts [data] input. | 3
| Angular | Create DynamicZoneComponent | @for sections + @if per __component value. @defer(on viewport) for heavy components. Unknown components silently skipped. | 3
| Angular | Setup NgOptimizedImage | Replace <img> tags with NgOptimizedImage for lazy loading and no CLS. | 2
Day 8 | Angular | Create PageComponent + routing | Calls ApiService on init. Passes sections[] to DynamicZoneComponent. Route: /pages/:slug. | 2
| Angular | Setup server.routes.ts | Define SSR vs client-side routes. | 2
| Angular | Setup TransferState | Prevent double HTTP calls — server fetches data, transfers to browser, browser reuses. | 2
| Angular | Test all components render | Each Dynamic Zone component type renders correctly with real Strapi data. | 2
Day 9 | Integration | Run full stack together | Start Redis, Strapi, .NET, Angular. Test cold start end to end. | 2
| Integration | Test caching flow | Hit page twice — second call faster. redis-cli keys * confirms cache populated. | 2
| Integration | Test ISR flow | Wait for TTL to expire. Confirm stale content served instantly, background refresh updates cache. | 2
| Integration | Test webhook purge flow | Publish in Strapi → webhook fires → .NET clears cache → next request fetches fresh content. | 2
Day 10 | Testing | Fix bugs from Day 9 | Handle edge cases: Strapi down, Redis down, unknown component, empty sections array. | 3
| Testing | Performance check | Measure response times with cache ON vs OFF. | 2
| Testing | Code cleanup + README | Remove debug code. Write README with run instructions and architecture overview. | 2
| Testing | Demo full flow | End-to-end demo: Strapi publish → webhook → cache purge → fresh content in Angular. | 1
Total Estimated Hours